## Part 1 Scope
FICTIONAL EXAMPLE — illustrative shop only
System and boundary | Fictional 40-person machine shop; cloud workspace with CUI drawings and CNC machines | The systems that handle CUI, with a pointer to the boundary in your system security plan (SSP) — NIST: a clearly defined boundary is "a prerequisite for effective risk assessments"
In scope, excluded, unknown | Unknown / not supplied | Asset groups, applications, and outside providers in scope; exclusions with the reason; unknowns with an owner and a due date — 32 CFR 170.19: be prepared to justify out-of-scope assets; the unknowns/owner/due-date fields are our tracking aids
Specialized assets | CNC controller; document in inventory, SSP, and network diagram | Shop-floor machines, test equipment, and other operational technology, and how each is managed — 170.19 Table 3
Risk assessment interval | Every 12 months | Your actual interval, no longer than one year; for example, "every 12 months," plus any extra triggers you choose — Objective 3.11.1[a]; one-year ceiling in 170.4
This assessment / previous / next due | Unknown / not supplied | Three dates — Objective 3.11.1[b]; the three-date layout is our way to show the history and next due date
Scan intervals | Monthly, plus relevant new vulnerabilities | Defined interval for systems and for applications; they may be the same — Objective 3.11.2[a]
New-vulnerability process | Unknown / not supplied | Which advisory sources you watch, who decides whether they apply, who triggers the scan — Objectives 3.11.2[d] and [e]
Method and rating scale | Illustrative Low / Medium / High; criteria remain to be documented | Your criteria for likelihood, impact, and any overall rating. For example: documented Low / Medium / High descriptions informed by NIST SP 800-30 Rev. 1 — DoD: use established criteria and procedures; NIST SP 800-30 "provides guidance"
Inputs used | Unknown / not supplied | Date of latest scans, inventory version, incident log, list of outside providers — DoD: a vulnerability assessment is an input; NIST: consider external parties
Performed by / approved by | Unknown / not supplied | Names, roles, and dates; record review/approval under your document-control procedure — 32 CFR 170.24(b)(1): evidence must be final; unapproved policies are unacceptable. The approval-record field is our recommended tracking aid
Assumptions and unresolved information | Printer coverage unresolved; owner/date not supplied | Record assumptions, uncertainty, and facts still being resolved; assign an owner and due date where appropriate.

## Part 2 Risk Register
FICTIONAL EXAMPLE — illustrative shop only | [7 empty] | Outside party involved | Decision | Proof of action | Risk after verified action | Assumptions / uncertainty / evidence sources
R-01 | Phishing email steals an engineer's password | People click links | Cloud workspace with CUI drawings | Multifactor sign-in; awareness training | High | High | Reduce: phishing-resistant sign-in for engineers and admins; IT lead; 60 days | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied
R-02 | Malware reaches a CNC controller on a USB stick | Controller runs an old operating system that can't be patched | Machine receiving CUI programs | Separate network segment | Medium | Medium | Reduce: lock down USB media. Record as a specialized asset in the inventory, SSP, and network diagram | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied
R-03 | MSP's remote-access tool is compromised | MSP holds admin access to everything | All CUI systems | MSP accounts need multifactor; access is logged | Medium | High | Reduce: limit the tool to named devices; review the MSP's responsibility matrix | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied
R-04 | Attackers exploit a newly identified VPN (virtual private network) flaw | Patch not yet applied | Remote access into the CUI environment | Scanning; VPN limited to staff accounts | High | High | Reduce: disable the affected VPN immediately; patch within the shop's 7-day outer limit before restoring it (traced below) | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied
R-05 | A drawing is emailed to the wrong customer | Similar names in the address book | CUI drawings; trust with the prime | CUI marking; training | Medium | High | Reduce: share CUI only through the approved workspace; block CUI folders from email attachments | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied
R-06 | Laptop with CUI stolen from a truck | Staff travel with CUI | One laptop | Verified full-disk encryption using a FIPS-validated module; powered off, keys not with the laptop | Medium | Low | Accept the residual risk under those checked assumptions; owner signs and dates; mandatory safeguards and incident duties still apply | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied

## Part 3 Scan Log
FICTIONAL EXAMPLE — illustrative shop only
ADV-07, Day 1 | Day 1 | ADV-07 | The VPN vendor posts an advisory; the flaw is being actively exploited. | The VPN vendor posts an advisory; the flaw is being actively exploited. | Unknown / not supplied | Unknown / not supplied
AP-07, Day 1 | Day 1 |  | The inventory shows the shop's VPN runs an affected version. | The inventory shows the shop's VPN runs an affected version. | Unknown / not supplied | Unknown / not supplied
SC-31, Day 1 | Day 1 |  | A scan confirms finding F-114 on the VPN. | A scan confirms finding F-114 on the VPN. | Unknown / not supplied | Unknown / not supplied
R-04, Day 1 | Day 1 |  | Rated High / High. Disable the affected VPN immediately. Patch within the 7-day outer limit before restoring access; named-user restrictions alone do not address this fictional exploit. | Rated High / High. Disable the affected VPN immediately. Patch within the 7-day outer limit before restoring access; named-user restrictions alone do not address this fictional exploit. | Unknown / not supplied | Unknown / not supplied
CH-22, Day 3 | Day 3 |  | Patch applied in an approved change window. | Patch applied in an approved change window. | Unknown / not supplied | Unknown / not supplied
SC-32, Day 3 | Day 3 |  | Re-scan no longer detects F-114; version confirmed before access is restored. | Re-scan no longer detects F-114; version confirmed before access is restored. | Unknown / not supplied | Unknown / not supplied
R-04, Day 3 | Day 3 |  | Re-rated. Remote access stays on the register as a standing risk. | Re-rated. Remote access stays on the register as a standing risk. | Unknown / not supplied | Unknown / not supplied
SC-30 | Unknown / not supplied | Scheduled scan | Networked printer expected but absent from successful coverage | Printer coverage is unresolved | Unknown / not supplied | Owner/date not supplied

## Part 4 Evidence Index
FICTIONAL EXAMPLE — illustrative shop only
3.11.1[a] Interval defined | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Review against the applicable objective
3.11.1[b] Risk assessed at that interval | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Review against the applicable objective
3.11.2[a] Scan interval defined | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Review against the applicable objective
3.11.2[b] Systems scanned on schedule | Needs review | Unknown / not supplied | Unknown / not supplied | Review against the applicable objective
3.11.2[c] Applications scanned on schedule | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Review against the applicable objective
3.11.2[d] Systems scanned on new vulnerabilities | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Review against the applicable objective
3.11.2[e] Applications scanned on new vulnerabilities | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Review against the applicable objective
3.11.3[a] Vulnerabilities identified | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Review against the applicable objective
3.11.3[b] Remediated per risk assessment | Unknown / not supplied | Unknown / not supplied | Unknown / not supplied | Review against the applicable objective